## Sheet1
[7 empty] | Brian | Debbie | Issac | Linden | Michelle
|  |  | Role | Owner | Estimated | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | By Task | By Task | By Task | By Task | By Task | By Task
Iteration 3
Documentation
| Primary Task | Architecture Document
| Subtasks | Introduction | Project Manager | Linden | 1 | 0.25 |  |  |  | 0.25
|  | Design Goals | Project Manager | Linden | 1 | 0.25 |  |  |  | 0.25
|  | System Behavior | Project Manager | Linden | 2 | 0.25 |  |  |  | 0.25
|  | Logical View | Project Manager | Linden | 2 | 2 |  |  |  | 2
|  | Class Diagrams | Developer | Issac, Debbie | 2 | 4.5 |  |  | 1 | 1.75
|  | Process View | Project Manager | Linden | 2 | 2 |  |  |  | 2
|  | Development View | Project Manager | Linden | 2 | 2 |  |  |  | 2
|  | Physical View | Project Manager | Linden | 2 | 0.5 |  |  |  | 0.5
|  | Use Case View | Project Manager | Linden | 2 | 0.5 |  |  |  | 0.5
Coding
|  | Notifcation Database | Developer | Brian | 2 | 3 | 3
|  | Notification Access Service | Developer | Brian | 1 | 1 | 1
| Primary Task | Username/Password Database
| Subtasks | - Create new database for logging in | Team | Linden, Brian, Debbie, Issac, Michelle | 3 | 0
|  | - Create table for users with their passwords | Team | Linden, Brian, Debbie, Issac, Michelle | 1 | 0
|  | - Create connection to login table in api/c# program | Team | Linden, Brian, Debbie, Issac, Michelle | 2 | 0
|  | - Give access to commerceDB on successful login | Team | Linden, Brian, Debbie, Issac, Michelle | 2 | 0
|  | - Password hashing? | Team | Linden, Brian, Debbie, Issac, Michelle | 2 | 0
|  | Determine Account Type by Account Number ? | Developer | Brian | 2 | 0
| Primary Task | Frontend: Mock Notification Data & create menu
| Subtasks | Create json file of notifications, match api/db models | Tech Lead | Michelle | 2 | 1 |  |  |  |  | 1
|  | Create notification entity/object | Tech Lead | Michelle | 1 | 1 |  |  |  |  | 1
|  | Service to read in Notification data and convert to objects | Tech Lead | Michelle | 2 | 2 |  |  |  |  | 2
|  | Notification Menu component in header | Tech Lead | Michelle | 2 | 2 |  |  |  |  | 2
|  | Popover component for notification details/listing | Tech Lead | Michelle | 2 | 2 |  |  |  |  | 2
| Primary Task | Frontend: Create Account entity/sign in & out capability
| Subtasks | Create user/account object | Developer | Debbie | 1 |  |  | 1
|  | Create Avatar component in header | Developer | Debbie | 1 |  |  | 2
|  | Create Menu component from avatar - sign in/out | Developer | Debbie | 1 |  |  | 1
|  | Research React libraries for signing in/out | Developer | Debbie | 3 |  |  | 2
| Primary Task | Frontend: Expand Transaction Table capability
| Subtasks | Ability to add transaction | Tech Lead | Michelle | 2 | 0
|  | Match Prototype for transaction table | Tech Lead | Michelle | 2 | 0
Iteration 3 Total |  |  |  |  | 46 | 24.25 | 4 | 6 | 1 | 9.5 | 8