## Sheet1
Task Name: (Dependencies top to bottom) | [6 empty] | Brian | Debbie | Issac | Linden | Michelle
|  |  | Role | Owner | Estimated | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | By Task | By Task | By Task | By Task | By Task | By Task
Iteration 1
Research
| Primary Task | Determine technology requirements
| Subtasks | - Determine a suitable web development framework | Tech Lead | Michelle | 1 | 1 |  |  |  |  | 1
|  | - Determine a suitable SQL or NoSQL database | Developer | Brian | 1 | 1 | 1
|  | - Determine a CSS framework | Tech Lead | Michelle | 1 | 1 |  |  |  |  | 1
|  | - Begin learning new languages and environments | Project Manager, Devoloper | Linden, Brian, Debbie, Issac | 5 | 12 | 1 | 6 |  | 5
|  | -Research Token Authentication | Developer | Isaac | 3 | 2 |  |  | 2
|  | Sketch out UI | Developer | Debbie | 2 | 2 |  | 2
Documentation
|  | Project Charter | Project Manager, Developers | Linden | 2 | 2 |  |  |  | 2
| Primary Task | Requirements Document (Project Plan)
| Subtasks | - Overview of the application | Project Manager, Developers | Linden, Brian, Debbie, Issac | 2 | 4 | 2 | 1 | 1
|  | - Technical Requirements and tech stack specification | Tech Lead | Michelle | 1 | 1 |  |  |  |  | 1
|  | - Requirements summarized and priority specified | Project Manager, Developers | Linden, Debbie, Issac | 2 | 5 |  | 2 | 1 | 2
|  | - Requirements are measurable and testable | Project Manager, Developers | Linden | 2 | 1 |  |  |  | 1
|  | - Determine Use Cases | Project Manager | Linden | 2 | 3 |  |  |  | 3
|  | - Determine Constraints | Project Manager | Linden | 1 | 1 |  |  |  | 1
|  | - Plan Stretch Goals | Team | Brian, Debbie, Issac, Linden, Michelle | 1 | 2 | 1 |  |  | 1
| Primary Task | Iteration 1 Review | Project Manager | Linden | 1 | 1 |  |  |  | 1
Coding
|  | Environment Setup | Tech Lead | Michelle | 2 | 4 |  |  |  |  | 4
|  | Setup server | Developer | Michelle | 2 | 2 |  |  |  |  | 2
|  | Setup database | Developer | Brian | 2 | 2 | 2
|  | Verify endpoints successfully connected | Tech Lead | Michelle | 1 | 2 |  |  |  |  | 2
|  | Build empty React app | Tech Lead | Michelle | 1 | 2 |  |  |  |  | 2
v
Iteration 1 Total |  |  |  |  | 35 | 51 | 7 | 11 | 4 | 16 | 13