## Sheet1
Task Name: (Dependencies top to bottom) | [6 empty] | Brian | Debbie | Issac | Linden | Michelle
|  |  | Role | Owner | Estimated | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | By Task | By Task | By Task | By Task | By Task | By Task
Iteration 1
Research
| Primary Task | Determine technology requirements
| Subtasks | - Determine a suitable web development framework | Tech Lead | Michelle | 1 | 1 |  |  |  |  | 1
|  | - Determine a suitable SQL or NoSQL database | Developer | Brian | 1 | 1 | 1
|  | - Determine a CSS framework | Tech Lead | Michelle | 1 | 1 |  |  |  |  | 1
|  | - Begin learning new languages and environments | Project Manager; Devolopers | Linden, Brian, Debbie, Issac | 5 | 12 | 1 | 6 |  | 5
|  | -Research Token Authentication | Developer | Isaac | 3 | 2 |  |  | 2
|  | Sketch out UI | Developer | Debbie | 2 | 2 |  | 2
Documentation
|  | Project Charter | Project Manager; Developers | Linden | 2 | 2 |  |  |  | 2
| Primary Task | Requirements Document (Project Plan)
| Subtasks | - Overview of the application | Project Manager; Devolopers | Linden, Brian, Debbie, Issac | 2 | 4 | 2 | 1 | 1
|  | - Technical Requirements and tech stack specification | Tech Lead | Michelle | 1 | 1 |  |  |  |  | 1
|  | - Requirements summarized and priority specified | Project Manager; Devolopers | Linden, Debbie, Issac | 2 | 5 |  | 2 | 1 | 2
|  | - Requirements are measurable and testable | Project Manager; Devolopers | Linden | 2 | 1 |  |  |  | 1
|  | - Determine Use Cases | Project Manager | Linden | 2 | 3 |  |  |  | 3
|  | - Determine Constraints | Project Manager | Linden | 1 | 1 |  |  |  | 1
|  | - Plan Stretch Goals | Team | Brian, Debbie, Issac, Linden, Michelle | 1 | 2 | 1 |  |  | 1
|  | Iteration 1 Review | Project Manager | Linden | 1 | 1 |  |  |  | 1
Coding
|  | Environment Setup | Tech Lead | Michelle | 2 | 4 |  |  |  |  | 4
|  | Setup server | Developer | Michelle | 2 | 2 |  |  |  |  | 2
|  | Setup database | Developer | Brian | 2 | 2 | 2
|  | Verify endpoints successfully connected | Tech Lead | Michelle | 1 | 2 |  |  |  |  | 2
|  | Build empty React app | Tech Lead | Michelle | 1 | 2 |  |  |  |  | 2
Iteration 1 Total |  |  |  |  | 35 | 51 | 7 | 11 | 4 | 16 | 13
[7 empty] | Brian | Debbie | Issac | Linden | Michelle
|  |  | Role | Owner | Estimated | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | By Task | By Task | By Task | By Task | By Task | By Task
Iteration 2
Documentation
| Primary Task | Project Plan
| Subtasks | Section 1 | Project Manager; Devolopers | Linden, Debbie | 1 | 1 |  | 1 |  | 1
|  | Section 2 | Project Manager; Devolopers | Linden, Debbie | 1 | 2 |  | 1 |  | 1
|  | Section 3 | Project Manager | Linden | 1 | 1 |  |  |  | 1
|  | Section 4 | Project Manager | Linden | 2 | 2 |  |  |  | 2
|  | Section 5 | Project Manager; Devolopers | Linden, Brian, Issac | 2 | 2.5 | 0.5 |  |  | 2
|  | GitHub Assigning Issue; Managing milestones, etc | Project Manager | Linden | 1 | 0.5 |  |  |  | 0.5
Presentation
|  | Iteration 2 Presentation | Team | Linden, Brian, Debbie, Issac, Michelle | 2 | 5.5 | 1 | 1 | 0.5 | 2 | 1
Design
|  | Protoype UI | Developer | Debbie | 6 | 6 |  | 6
Coding
|  | C# program to read in file and store transaction objects | Project Manager | Linden | 2 | 2 |  |  |  | 2
|  | Create a temporary access service | Project Manager | Linden | 1 | 1 |  |  |  | 1
|  | Create interface for the data access service | Project Manager | Linden | 3 | 3 |  |  |  | 3
| Primary Task | Restructure database | Developer | Brian |  | 4 | 4
| Subtasks | - Reformat transaction table | Developer | Brian | 1 | 1 | 1
|  | - Consider user permissions | Developer | Brian | 1 | 0.5 | 0.5
|  | - Stored procedure for viewing transactions | Developer | Brian | 1 | 0.5 | 0.5
|  | C# program to take stored objects and send to DB | Developer | Brian | 1 | 2 | 2
|  | Begin learning using C# commands with dotnet API | Developer | Brian | 3 | 1 | 1
| Primary Task | Create login table | Developer | Issac | 1
| Subtasks | - Hashing for passwords | Developer | Issac | 3
|  | Implement UI Components in React App | Tech Lead; Developer | Michelle, Debbie | 6 | 6 |  |  |  |  | 6
|  | Technical Prototype in React | Tech Lead | Michelle | 5 | 5 |  |  |  |  | 5
|  | Local dev env set up on all Developer computers | Team | Linden, Brian, Debbie, Issac, Michelle | 5 | 3.5 | 1 | 1.5 | 0.5 | 1
Iteration 2 Total |  |  |  |  | 49 | 50 | 11.5 | 10.5 | 1 | 16.5 | 12
[7 empty] | Brian | Debbie | Issac | Linden | Michelle
|  |  | Role | Owner | Estimated | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | By Task | By Task | By Task | By Task | By Task | By Task
Iteration 3
Documentation
| Primary Task | Architecture Document
| Subtasks | Introduction | Project Manager | Linden | 2
|  | Design Goals | Team | Linden, Brian, Debbie, Issac, Michelle | 2
|  | System Behavior | Team | Linden, Brian, Debbie, Issac, Michelle | 2
|  | Logical View | Tech Lead | Michelle | 2
|  | Process View | Tech Lead | Michelle | 2
|  | Development View | Team | Linden, Brian, Debbie, Issac, Michelle | 2
|  | Physical View | Team | Linden, Brian, Debbie, Issac, Michelle | 2
|  | Use Case View | Team | Linden, Brian, Debbie, Issac, Michelle | 2
Coding
|  | Notifcation Database | Developer | Brian | 2
|  | Notification Access Service | Developer | Brian | 1
| Primary Task | Username/Password Database
| Subtasks | - Create new database for logging in | Team | Linden, Brian, Debbie, Issac, Michelle | 3
|  | - Create table for users with their passwords | Team | Linden, Brian, Debbie, Issac, Michelle | 1
|  | - Create connection to login table in api/c# program | Team | Linden, Brian, Debbie, Issac, Michelle | 2
|  | - Give access to commerceDB on successful login | Team | Linden, Brian, Debbie, Issac, Michelle | 2
|  | - Password hashing? | Team | Linden, Brian, Debbie, Issac, Michelle | 2
|  | Determine Account Type by Account Number ? | Developer | Brian | 2
| Primary Task | Frontend: Mock Notification Data & create menu
| Subtasks | Create json file of notifications, match api/db models | Tech Lead | Michelle | 2
|  | Create notification entity/object | Tech Lead | Michelle | 1
|  | Service to read in Notification data and convert to objects | Tech Lead | Michelle | 2
|  | Notification Menu component in header | Tech Lead | Michelle | 2
|  | Popover component for notification details/listing | Tech Lead | Michelle | 2
| Primary Task | Frontend: Create Account entity/sign in & out capability
| Subtasks | Create user/account object | Developer | Debbie | 1
|  | Create Avatar component in header | Developer | Debbie | 1
|  | Create Menu component from avatar - sign in/out | Developer | Debbie | 1
|  | Research React libraries for signing in/out | Developer | Debbie | 3
| Primary Task | Frontend: Expand Transaction Table capability
| Subtasks | Ability to add transaction | Tech Lead | Michelle | 2
|  | Match Prototype for transaction table | Tech Lead | Michelle | 2
Iteration 3 Total |  |  |  |  | 46 | 0 | 0 | 0 | 0 | 0 | 0