## Sheet1
|  |  | Role | Owner | Estimated | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | By Task | By Task | By Task | By Task | By Task | By Task
Iteration 4
Documentation
| Primary Task | Test Plan Document
| Subtasks | Test Plan | Project Manager | Linden | 2
|  | Test Specifications | Project Manager | Linden | 2
|  | Test Reports | Project Manager | Linden | 2
*Need to start not | Primary Task | User and System Guide
not due til | Subtasks | User | Developer | Debbie, Michelle
mid-Iteration 5 |  | System | Project Manager | Linden, Brian, Issac
Coding
|  | Reformat Transaction to include location and time | Developer | Brian | 0.5
|  | Create and test triggers for time and location | Developer | Brian | 1
|  | Connect API layer to frontend and test functionality | Developer, Tech Lead | Brian, Michelle | 2
|  | Display notifications as JSON for front end retrieval | Developer | Brian | 1.5
| Primary Task | Username/Password Database
| Subtasks | - Create new database for logging in | Team | Linden, Brian, Debbie, Issac, Michelle | 3
|  | - Create table for users with their passwords | Team | Linden, Brian, Debbie, Issac, Michelle | 1
|  | - Create connection to login table in api/c# program | Team | Linden, Brian, Debbie, Issac, Michelle | 2
|  | - Give access to commerceDB on successful login | Team | Linden, Brian, Debbie, Issac, Michelle | 2
|  | - Password hashing? | Team | Linden, Brian, Debbie, Issac, Michelle | 2
| Primary Task | Unit Testing
| Subtasks | at lteast 10% of code needs unit tests (required) | Project Manager | Linden | 3
| Primary Task | Login Page | Developer | Debbie
| Primary Task | Integrate API endpoints w front end
| Subtasks | -get API running locally on front end dev machines | Tech Lead | Michelle | 2
|  | -test base API endpoint connection | Tech Lead | Michelle | 1
|  | - Add Axios to front end for calls | Tech Lead | Michelle | 1
|  | - Add service calls to API | Tech Lead | Michelle | 3
|  | -Add service functions to iterate through API calls | Tech Lead | Michelle | 2
|  | Testing: wrap Axios calls with error handling for 500 response | Tech Lead | Michelle, Linden | 2
| Primary Task | Frontend: Expand Transaction Table capability
| Subtasks | Ability to add transaction | Tech Lead | Michelle | 2
|  | Match Prototype for transaction table | Tech Lead | Michelle | 2
Iteration 4 Total |  |  |  |  | 39 | 0 | 0 | 0 | 0 | 0 | 0