## Sheet1
[7 empty] | Brian | Debbie | Issac | Linden | Michelle
|  |  | Role | Owner | Estimated | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | By Task | By Task | By Task | By Task | By Task | By Task
Iteration 5
Documentation
| Primary Task | User and System Guide
| Subtasks | User | Developer | Debbie, Issac | 4
|  | System | Project Manager | Linden | 3
Coding
|  | Add GUID into notification table | Developer | Brian | 0.5
|  | Review backend code - clean up as needed | Developer | Brian | 1
| Primary Task | Integrate API endpoints w front end
| Subtasks | -get API running locally on front end dev machines | Tech Lead | Michelle | 2
|  | -test base API endpoint connection | Tech Lead | Michelle | 1
|  | - Add Axios to front end for calls | Tech Lead | Michelle | 1
|  | - Add service calls to API | Tech Lead | Michelle | 3
|  | -Add service functions to iterate through API calls | Tech Lead | Michelle | 2
|  | Testing: wrap Axios calls with error handling for 500 response | Tech Lead | Michelle | 2
| Primary Task | Username/Password DB - Firebase
| Presentation | Video presentation | Team | Linden, Brian, Debbie, Issac, Michelle | 3
Iteration 5 Total |  |  |  |  | 22.5 | 0 | 0 | 0 | 0 | 0 | 0