## Sheet1
Task Name: (Dependencies top to bottom) | [7 empty] | Brian | Debbie | Issac | Linden | Michelle
|  |  | Role | Owner | Estimated | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task
Iteration 1
Research
| Primary Task | Determine technology requirements | Tech Lead | Michelle | 2
| Subtasks | - Determine a suitable web development framework | Tech Lead | Michelle | 1
|  | - Determine a suitable SQL or NoSQL database | Developer | Brian | 1
|  | - Determine a CSS framework | Tech Lead | Michelle | 1
|  | - Begin learning new languages and environments | Project Manager, Devoloper | Brian, Debbie, Issac, Linden | 5
|  | -Research Token Authentication | Developer | Isaac | 3
|  | -Sketch out UI | Developer | Debbie | 2
Documentation
|  | Project Charter | Project Manager, Developers | Linden, Brian, Debbie, Issac | 2
| Primary Task | Requirements Document (Project Plan) | Project Manager, Developers | Linden, Brian, Debbie, Issac | 12
| Subtasks | - Overview of the application | Project Manager, Developers | Linden, Brian, Debbie, Issac | 2
|  | -Technical Requirements and tech stack specification | Tech Lead | Michelle | 1
|  | - Requirements summarized and priority specified | Project Manager, Developers | Linden, Brian, Debbie, Issac | 2
|  | - Requirements are measurable and testable | Project Manager, Developers | Linden, Brian, Debbie, Issac | 2
|  | - Determine Use Cases | Team | Brian, Debbie, Isaac, Linden, Michelle | 2
|  | - Determine Constraints | Project Manager | Linden | 2
|  | - Plan Stretch Goals | Team | Brian, Debbie, Issac, Linden, Michelle | 1
Coding
| Primary Task | Environment Setup | Tech Lead | Michelle | -
| Subtasks | Setup server | Developer | Brian | 2
|  | Setup database | Developer | Brian | 1
|  | Verify endpoints successfully connected | Tech Lead | Michelle | 1
|  | Build empty React app | Tech Lead | Michelle | 1
Total |  |  |  |  | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10% code coverage for unit tests. xUnit is a good framework for .NET.
(continued)
Stretch Goals (Two are required)
|  | 1 | Deploy the project into a windows server/cloud instance
|  | a. | Practice configuration properties for different environments
|  | 2 | Create a Web API layer for backend interactions.
|  | 3 | Use an open source reporting tool/business intelligence suite for all the reporting and its data visualization
|  | 4 | Use version control throughout the project
|  | 5 | Security scan your application and fix Critical issues at a minimum. OWASP ZAP is a good open source option
|  | 6 | Use Commerce Bank color scheme in styling
|  | 7 | Session for remembering user if they close their browser and then log in again
|  | 8 | Options for user if they forgot their username or password
|  | 9 | Notifications via messaging center in the app
|  | 10 | Notifications via email or text